**5th Video Conference 1st March 2021**

The fifth meeting was held via videoconference using the Zoom platform on the above date at 1600 Hrs CET.

This meeting was previously agreed for the 22nd February 2021 and was rearranged at the request of the participants from Spain. During this meeting all leading coordinators from the 5 countries were present and were able to speak on a range of topics.

1. The meeting started with a suggestion to try and extend the project due the current Covid-19 pandemic. All participants agreed that the idea was good and the Czech Republic then informed all participants that an extension should not be applied until at least the end of this current school year. This was at the recommendation of the Czech National Agency. Therefore, an extension would be looked into with the agreement of the overall leader of the project, the Headmaster of the Zš UNESCO, Czech Republic. During this part of the meeting it was mentioned that no one had information as to when mobilities might be able to start occurring and the requirements in place for the travel of students and teachers.
2. The next item was to ask everyone to make sure that all work from C1 was uploaded to Google Drive so it could be placed onto the website. Due to the differences in the way National lock-downs are working, there has been a slight delay with some of this work and it will be uploaded on completion.
3. As a result of the slight delays mentioned in minute 2, there was another suggestion to slow down the current workload. It was explained that there are a few problems with timings and trying to assemble students together at the same time as different timetables are an issue at present. Therefore, it was agreed that we would only carry out all of the work for C1 and C2 this current school year. With C1 nearly completed therefore we would extend the work of C2 to be completed by the end of June. Meaning that C3 would now start in September of this year and not in this current school year.
   1. C1+C2 completed by June 2021
   2. C3-C5 start September 2021
4. Next was the briefing about the C2 work. Information was shared so all participants could see how the tasks had been setup on Google Drive. The January task was about “Food Waste”, where students had to complete the questions and upload the answers so they can be collated by Denmark. The next item was a task about creating a campaign on ways to reduce food waste and food loss. The coordinator from Denmark also spoke about how they had taken out of date food from a shop and turned it into meals. Also, it was mentioned about some food is used through a food chain. These two items where meant to be the work for March and April but had not been placed on the drive yet.
5. With the extension of this phase of the project it was decided that the video conferences would take place in June instead of April. It would then be the responsibility of the individual participants to arrange their conferences. The pairings for the conferences are as follows:
6. Denmark – Portugal
7. Portugal – Czech Republic
8. Czech Republic – Spain
9. Spain – Netherlands
10. Netherlands – Denmark
11. The next meeting is scheduled to take place on Monday 19th April 2021 at 1600 hrs CET.