**“HAPPY, HEALTHY, WISE AND WEALTHY”**

**Procedure:**

1. All the countries are to find an environmental problem/topic they want to study in more depth.
2. The first topic will be, “The Recycling Scheme in our Country” (chosen by the Czech Republic).
3. This topic will be discussed by all the countries, subsequently coordinated by the Czech Republic for 4 months and end up with a mobility to the Czech Republic.
4. All the countries will get a **“to do list”** from the Czech Republic – tasks to be completed before the first mobility.
5. During the 4 month period before prior to any mobility, students will be in contact and completing the tasks set out in the application form (all of this will be coordinated by the country which has chosen the topic).
6. Every partner state will be responsible for their respective topics and results relating to the project.
7. All the activities will be supervised by the Czech Republic as the main coordinator.

**“TO DO LIST” from the Czech Republic**

**Topic: “**Recycling Schemes in European Schools and Households”

**Task No.1 (September 2020)**

1. Mapping the recycling scheme at my school and in my country - (taking pictures, describing different types of waste, bins, explanation of the recycling scheme and process in our region and country).
2. Research as to recycling in households - creating a questionnaire (to be answered by 30 households in the country), gathering the results, evaluation.
3. Taking pictures *-* in order to create a comic story later.

**Task No.2 (October 2020)**

Working on a PowerPoint presentation

* Recycling scheme in the country.
* Recycling procedures at my school.
* Recycling in our households.

Creating a short comic story:

Students will create a short comic story reflecting the recycling situation in their country/at their school. The comic will be created with the photos that were taken in the previous task.

**Task No.3 (November 2020)**

The students from one country will send their presentation to students from another country in order for them to be studied by the receiving partner. (Distribution to follow)

Then the pupils of two schools will get in touch via videoconferencing, eTwinning, e-mail, phone, Skype, Facebook (according to individual preference).

During this phase they will discuss, explain, specify and add details to all the issues that were not obvious from the presentation. The goal is to understand the recycling scheme, procedures, as well as the pros and cons of the foreign recycling policies.

The Czech Republic will send the presentation to Denmark.

Denmark will send the presentation to Spain.

Spain will send the presentation to Portugal.

Portugal will send the presentation to Netherlands.

Netherlands will send the presentation to the Czech Republic.

**Contents of the Mobility (December 2020)**

Workshop No.1

This workshop is where each partner will present their own countries recycling policies. (Students to be arranged into small groups of 10)

Workshop No.2

This workshop is going to be the introduction of the comic stories from Task 2 and possible ways to improve them. (All students and teachers to take part)

Workshop No.3

The creation of posters with pictures, photos, quotes, logos, slogans, catchwords and their presentation (groups of 3 students, mixed nationalities), topic: **“How to Motivate People to Produce Less Waste”**.

Workshop No.4

A trip to **Kovozoo,** a unique zoo that is trying to show how useless waste can be turned into something for the benefit the community.

Workshop No.5

This workshop is a trip to learn about and visit a Recycling and Incineration Plant within the region**.**

Workshop No.6

There will be an excursion to **Hostětín**, an eco-village previously visited by Prince Charles. Here it is possible to see a model project that shows how to start preparing for a sustainable future.

**Post Mobility Activities (January 2021)**

All of the project work that will have been carried out as part of the mobility is to be displayed in a public place where the information can be disseminated. This would be best in the form of an exhibition and is to include all presentations, comic books and posters produced before and during the stay in the Czech Republic.

The Czech Republic will also be responsible for the production of a newsletter to catalogue the experiences of the mobility. This should contain pictures and a form of diary about all of the events that take place during the week. This in turn is to be sent to all countries for display on completion.