## Slide 1: Videoconference_teachers_September 23, 2021

## Slide 2: Extension of the project
The end of the project now: August 31, 2022
Suggested end of the project: August 31, 2023
Does everybody agree?
MOBILITIES = till now we have not realized the following mobilities:
C1 = The CR (December 2020)
C2 = Denmark (April 2021)

## Slide 3
EXTENSION OF THE PROJECT:
ONE YEAR
START OF TRAVELLING:
THE CR = now (only vaccinated children are going to travel)
Spain = probably the new calendar year (negatively tested children, vaccinated children are going to travel)
The Netherlands = now (negatively tested children, vaccinated children are going to travel)
Denmark??
Portugal = mid- November (only vaccinated kids are going to travel, they have to be accommodated in vaccinated families)

## Slide 4: MOBILITIES AFTER EXTENSION? 5 pupils + 2 teachers
JANUARY 2022
(THE CZECH REPUBLIC)
MAY 2022
(DENMARK)
OCTOBER 2022
(SPAIN)
JANUARY 2023
(THE NETHERLANDS)
MAY 2023
(PORTUGAL)

## Slide 5: MOBILITIES AFTER EXTENSION?
Host families – negative tests/vaccination?
Other requirements?
Single sex students = shared bedrooms are ok
A boy + a girl together = no shared bedrooms?
COSTS:
1.Host families are providing the students with all the food (breakfast, snacks, lunches)?
2.The host country creates the programme in advance (with all the costs stated – e.g. Fees for tickets, travelling expenses etc.)
3.The host country will provide one lunch for the teachets for free?

## Slide 6: It is written by every partner, the deadline for the CR is September 30.
Interim report

## Slide 7: How is your project progressing so far? Is the implementation following the plan described in the project application? If plans had to be changed, please explain how and why.
Our project started on September 1, 2020, where all the partners tried really hard to ensure a successful beginning of the project: we created leaderships of the project in each of the countries, after that groups of students were chosen to take part in activities (Erasmus clubs), some of them filled personal forms in (profiles) in order to introduce themselves, others recorded short videos from the same reason. "To-do-lists" were created and shared, long-term work plan as well. We created a project web page, etwinning space, we started using facebook and instagram for dissemination reasons. Google disc files were set up with the purpose of instant sharing of our results. Padlet platform was introduced too. The responsibility for the dissemination activities was divided: The CR (is responsible for the project web page), The Netherlands (facebook and instagram), Portugal (Padlet), Spain (etwinning), Denmark (Google disc). A logo competition was organized, the winner was a Czech student. The first C1 mobility was connected with a lot of preparatory tasks and nearly all of them were finished (except for comic stories from Danish partner). All the videoconferences among the students took place as planned, similarly the videoconferences among the teachers (even if they were held a bit less frequently than planned because it was not needed to organize them more often). Nevertheless we were suffering from unability to travel due to the covid 19 pandemic and that prevent us from realizing the mobilities completely. Step by step all preparatory C2 activities needed more time (students were not able to get together e.g. to shoot a recipe video, to create campaign posters and food supply chain presentations, they had to communicate merely online after all the online lessons at school and their motivation was descending rapidly. According to the plan all the C2 activities/tasks were supposed to be finished in April 2021. Till now half of them is still not completed (especially by the Danish and Dutch partner). Some of the videoconferences among students were postponed until the beginning of the new school year 2021/2022. Moreover the C2 mobility is still waiting to be realized too. C3 tasks connected with Green space and urban settings (led by the Spanish partner) was started before the end of the school year by the Czech and Spanish school, other schools were struggling. The C3 mobility to Spain is definitely not going to take place as planned before. All in all, all the partners have agreed with the extension, so the Czech partner is going to ask for one more year prolongation.

## Slide 8: How is your project progressing so far? What was your school's contribution to the project so far?
As to the Czech coordinating school the problem with the time/tasks/activities was not so serious because we have only one project going on, so all the tasks were fulfilled more or less sucessfully on time. Preparatory tasks were not a problem, all the C1/C2 and partly C3 tasks have been finished, uploaded on the school web page, described in the school magazine etc. The students loved the videoconferences because they could see the foreign students "face to face" online at least. The truth is that it is really difficult when all the students work only online instead of gathering at school as a group. We have created Erasmus corner where the results of our efforts were displayed from time to time. The Czech school has led all the preparatory activities for the first C1 mobility successfully. The videoconferences among the students took place, the project web page was updated as well. We contributed (with the help of our partners) to etwinning, facebook, instagramm and google disc. The Czech leadership was trying to monitor what has been achieved in the project, adjust the plan when needed, communicate with the partners via e-mails, whatsapp or online, organize the videoconferences among the teachers and respond to changes - simply coordinate the whole project.

## Slide 9: How is your project progressing so far? What expenses did you cover with the funds spent until now?
We are in the middle of the project currently and due to pandemic of Covid 19 we have not realized any of the mobilities yet. That´s why all the "project management and implementation expenses" are connected only with the activities that are preparatory (other project events) so far and will later allow the occurance of the mobilities (all the partners prefer to realize the mobilities physically). The expenses include the following: paper and cartridge for copy machines (materials for students, the coordinator and Erasmus corner), plants, seeds, trees and bushes for revitalization of part of the school backyard (creation of a green space at school).

## Slide 10: Spain: to-do-list
Task No.1 (September/October)
Introduction. Spain introduces the topic with a presentation (summary) in which the topic to work is exposed: importance of green areas and urban trees for the improvement of quality of life and sustainability in the school and city environment.
Check our nearest green spaces. From here, each country should reflect on the public spaces close to the students in their day to day (squares, streets, schoolyard, ...).
Take images or videos (according to preference) of the spaces that will be studied to prepare a presentation later.
This phase should be used to reflect on the role that green spaces play and in what state they are. Questions can be raised such as: in our specific case, how do these spaces improve our quality of life? Are the spaces we have enough? What problems (if any) do we detect? What should be improved? Should I have more spaces in my neighborhood, or in my school?
It is an open work, in which each country can orient its analysis more towards some aspects than others, according to its reality.

## Slide 11: Spain: to-do-list
Task No.2 (September, October)
Working on a presentation
Students will prepare a presentation using the digital tool of their choice (Power Point, video, Genially, etc.). Here they will show the result of their research and reflection on the green spaces of their surroundings.
The presentation can include a final section with proposals for improvement (if any)

## Slide 12: Spain: to-do-list
Task No.3 (November)
Renaturalize a school space. Each country will create a green space in its educational center. The type of intervention may vary depending on the characteristics of each school. For example: create a small garden, plant some trees in the yard, recover a damaged garden, install planters, school garden, intervention in indoor spaces such as classrooms, etc.)
Images will be taken before and after the area where the action will be taken to document the process.

## Slide 13: Spain: to-do-list
Contents of the Mobility
Workshop No.1
The work done in task 2 (video, presentation) will be presented
Workshop No.2
Digital materials will be created to expose the benefits of woodland and green areas in urban settings and in the school environment. It can be an interactive image (Genially or similar), or the creation of posters or infographics.
Workshop No.3
Reforestation with native species in a degraded space. It will be held outside our center.
Workshop No.4
Visit to Sierra Espuña (Ricardo Codorniú Visitor Center) to discover a natural area that has become an example of forest recovery, after reaching a state of almost total loss of its vegetation cover at the end of the 19th century. It currently has several environmental protection figures for its high ecological value.

## Slide 14: VIDEOCONFERENCES THAT HAVE NOT BEEN REALIZED YET