## Slide 1: Videoconference coordinators meeting
26th June 2021
Cooperation for innovation and the exchange of good practices
KA229 - SCHOOL EXCHANGE PARTNERSHIPS
2020-1-CZ01-KA229-078153
“Happy, Healthy, Wise and Wealthy”

## Slide 2: Mobility Tool
The mid-term report has not been uploaded yet, we are going to write it in the middle of the project.

## Slide 3: OUR INTRODUCTORY TASKS
Creating project team at each school
Regular meetings of project teams
Videoconferences among coordinators
Creating Erasmus clubs (students taking part in Erasmus+ project)
Logo competition
eTwinning registration – is every partner uploading his/her materials there?
Facebook and Instagram

## Slide 4: OUR INTRODUCTORY TASKS
Sharing all the necessary documents on Google Drive
Creating Padlet
Introductory presentations/videos about schools
To – do – lists
Project web page
Dissemination

## Slide 5: ERASMUS CORNER (PHOTOS TO BE UPLOADED ON GOOGLE DISC) – we are going to need them for the final report

## Slide 6: Introductory personal video presentations – students (Google disc)
The Czech Republic – done (Questionnaires on Google disc, videos on etwinning)
Denmark – done
Portugal – done
The Netherlands – done
Spain - done

## Slide 7: C1: Recycling schemes in European schools and households
Household questionnaires – all countries have done them
Comic stories – missing: Denmark, The Netherlands
Recycling presentations - all countries have done them
Creating a comic book – waiting for all the comic stories (The CR)
VIDEOCONFERENCES AMONG STUDENTS
  Czech Republic and Denmark - done
  Denmark and Spain - ?
  Spain and Portugal - ?
  Portugal and The Netherlands - ?
  The Netherlands and Czech Republic - done

## Slide 8: C2: Food loss and waste reduction
Food waste questionnaires – all countries have done them (Denmark - results?)
Food supply chain presentations – missing: Denmark, The Netherlands
Campaign posters – missing: Denmark, The Netherlands
Food waste videos – missing: Portugal, The Netherlands
VIDEOCONFERENCES AMONG STUDENTS
Denmark – Portugal - ?
Portugal – Czech Republic – not completed (planned for September)
Czech Republic – Spain - done
Spain – Netherlands - ?
Netherlands – Denmark - ?

## Slide 9: C3: The importance of green areas in urban settings (to be finished in October 2021)
Introduction – research, discussions
Checking the nearest green spaces, taking images or videos
Creating presentations with proposals how to improve problematic sections
Green space creation + photos/videos
VIDEOCONFERENCES AMONG STUDENTS (September – October)
Denmark –
Portugal –
Czech Republic –
Spain –
Netherlands –

## Slide 10: Extension of the project
Czech NA says:
extension = one more year (the maximal allowed length)
the length can be shorter (2 months, half a year…)
- we have been advised to ask for extension at the beginning of the school year 2021/2022 (September)
all the partners have to agree with the extension
we have to give our reasons for extension
Our reasons (to be discussed):

## Slide 11: Mobilities
PLAN No.1
October 2021 - The CR
December 2021 - Denmark
February 2022 - Spain
April 2022 - The Netherlands
June 2022 - Portugal
PLAN No.2
(to be discussed)
The CR October 2021
Denmark?
Spain?
The Netherlands?
Portugal?

## Slide 12: ANY OTHER BUSINESS
?
THANKS FOR COMING
HAVE A GREAT DAY
