**6th Video Conference 3rd May 2021**

* **Original plan:**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | **THE CZECH REPUBLIC** | **DENMARK** | **SPAIN** | **THE NETHERLANDS** | **PORTUGAL** |
| **INTRODUCTION: SEPTEMBER 2020**  **INTRODUCTORY VIDEOS ABOUT SCHOOLS (needed for the mobilities – postponed until later)** | NO | NO | NO | NO | NO |
| **C1: OCTOBER 2020**  **FILLING IN THE HOUSEHOLD QUESTIONNAIRES + “RECYCLING” PRESENTATIONS** | YES | YES | YES | YES | YES |
| **C1: DECEMBER 2020**   * **COMIC STORIES (A COMIC BOOK)** | YES | NO | YES | NO | NO |
| **C1: DECEMBER 2020**   * **VIDEOCONFERENCES AMONG STUDENTS** | YES | YES | YES | YES | YES |
| **C2: JANUARY 2021**   * **FOOD WASTE RESEARCH** | YES | YES | YES | YES | YES |
| **C2: FEBRUARY 2021**   * **FOOD WASTE CAMPAIGN** | YES | NO | YES | NO | NO |
| **C2: MARCH 2021**   * **FOOD CHAINS** | YES | NO | NO | NO | NO |
| **C2: MARCH/APRIL 2021**   * **“MAKE FOOD FROM FOOD WASTE” VIDEOS** * **KAHOOT? – CROSSWORDS? – A VIDEO?** | NO | NO | YES | NO | NO |
| **C2 – APRIL 2021**   * **VIDEOCONFERENCES AMONG STUDENTS** * Denmark – Portugal * Portugal – Czech Republic * Czech Republic – Spain * Spain – Netherlands * Netherlands – Denmark |  |  |  |  |  |
| **C3 – MAY 2021 – to be commented by Spain** |  |  |  |  |  |

**- C2 Videoconferences in June? What about?**

* Evaluate your treatment of food at home and consider steps to reduce food waste in your family. Some of the students can keep track of and evaluate their efforts at reducing food waste at home.
* Task No.3 Working on a presentation:

a. Present yourself, your country, region, town and school

b. Present your findings about food waste and how to reduce it

c. Present the product you have chosen to follow in the food chain.

* **Asking NA for extension?**
* **Possibilities of travelling? When?**

**- July/August – mid-term report**

**- C3 – to be finished in October 2021**

*As a result of the slight delays mentioned in minute 2, there was another suggestion to slow down the current workload. It was explained that there are a few problems with timings and trying to assemble students together at the same time as different timetables are an issue at present. Therefore, it was agreed that we would only carry out all of the work for C1 and C2 this current school year. With C1 nearly completed therefore we would extend the work of C2 to be completed by the end of June. Meaning that C3 would now start in September of this year and not in this current school year.*

* 1. *C1+C2 completed by June 2021*
  2. *C3-C5 start September 2021*